## data
task_id | team | dependencies | task_group | task_description | start_date | end_date
1 | Business |  | Market Research | Conduct industry analysis | 2025-01-02 | 2025-01-06
2 | Finance |  | Budget Planning | Draft initial budget | 2025-01-03 | 2025-01-05
3 | Technology |  | System Design | Create architecture blueprint | 2025-01-04 | 2025-01-10
4 | Marketing |  | Brand Strategy | Define core messaging | 2025-01-05 | 2025-01-09
5 | Business | 1 | Market Research | Analyze competitor features | 2025-01-09 | 2025-01-12
6 | Finance | 2 | Budget Planning | Finalize funding allocation | 2025-01-10 | 2025-01-13
7 | Technology | 3 | System Design | Select tech stack | 2025-01-11 | 2025-01-16
8 | Marketing | 4 | Brand Strategy | Create style guide | 2025-01-12 | 2025-01-17
9 | Business |  | Vendor Management | Shortlist SaaS vendors | 2025-01-18 | 2025-01-20
10 | Technology | 7 | Dev Environment | Setup dev environment | 2025-01-19 | 2025-01-23
11 | Finance |  | Legal Compliance | Review contracts | 2025-01-24 | 2025-01-26
12 | Marketing |  | Content Creation | Write website copy | 2025-01-25 | 2025-01-30
13 | Technology | 10 | Core Development | Build authentication module | 2025-01-27 | 2025-02-01
14 | Business | 9 | Vendor Management | Negotiate contracts | 2025-01-31 | 2025-02-03
15 | Finance | 6 | Financial Systems | Set up accounting system | 2025-02-02 | 2025-02-06
16 | Technology |  | Testing Framework | Create test cases | 2025-02-07 | 2025-02-21
17 | Marketing |  | Social Media | Launch Twitter account | 2025-02-08 | 2025-02-10
18 | Business |  | Data Migration | Transfer customer data | 2025-02-13 | 2025-02-16
19 | Technology | 13 | Core Development | Implement payment gateway | 2025-02-14 | 2025-02-20
20 | Finance | 15 | Financial Systems | Process payroll integration | 2025-02-17 | 2025-02-21
21 | Marketing |  | Advertising | Design banner ads | 2025-02-22 | 2025-03-01
22 | Business |  | User Training | Create FAQ docs | 2025-02-23 | 2025-03-27
23 | Technology | 19 | Core Development | Build admin dashboard | 2025-02-28 | 2025-03-03
24 | Finance |  | Reporting | Generate financial statements | 2025-03-01 | 2025-04-06
25 | Marketing | 17 | Social Media | Schedule Q2 posts | 2025-03-07 | 2025-03-09
31 | Business |  | Launch Prep | Coordinate beta release | 2025-03-28 | 2025-03-30
32 | Finance |  | Payments | Enable billing system | 2025-03-31 | 2025-04-04
33 | Technology |  | Deployment | Production server setup | 2025-04-05 | 2025-04-07
34 | Marketing |  | Events | Plan launch webinar | 2025-04-06 | 2025-04-11
35 | Business | 31 | Launch Prep | Train support team | 2025-04-12 | 2025-04-14
36 | Technology | 33 | Deployment | Release v1.0 | 2025-04-17 | 2025-04-19
37 | Marketing | 34 | Events | Execute press release | 2025-04-20 | 2025-04-21
38 | Business |  | Analytics | Implement Mixpanel | 2025-04-24 | 2025-04-26
39 | Finance |  | Forecasting | Update revenue model | 2025-04-25 | 2025-04-28
40 | Technology |  | Maintenance | Hotfix deployment | 2025-03-25 | 2025-05-03
41 | Marketing |  | SEO | Optimize landing pages | 2025-05-04 | 2025-05-08
42 | Business |  | Partnerships | Sign reseller agreement | 2025-05-09 | 2025-05-11
43 | Finance |  | Investor Relations | Prepare board report | 2025-05-12 | 2025-05-15
44 | Technology |  | Optimization | Database indexing | 2025-05-16 | 2025-05-18
45 | Marketing |  | Retention | Create loyalty program | 2025-05-19 | 2025-05-23

## PROJECT
project_name | template_name | startline | buffer_days
Jembatan Medan | CES | 2026-07-01 | 0
Jembatan Medan | SD | 2026-07-01 | 0
Jembatan Medan | FT | 2026-07-01 | 0
Jembatan Jakarta | CES | 2026-07-01 | 0
Jembatan Jakarta | SD | 2026-07-01 | 0
Jembatan Jakarta | FT | 2026-07-01 | 0

## CES
task_id | dependencies | task_group | task_description | duration_days | role
1 |  | Section & Material Input | Defining section and material properties | 2 | CES Engineer
2 | 1 | Stucture Geometry | Construct structural frame | 3 | CES Engineer
3 | 2 | Boundary Condition | Define supports and links | 1 | CES Engineer
4 | 1 | SSI Parameter | Define supports and links | 3 | Supporting Engineer
5 | 3 | Tendon Input | Input tendon profile | 3 | CES Engineer
6 | 5 | Bridge Loading | Define bridge loads, construction and service loading | 4 | CES Engineer
7 | 6 | Construction Sequence Model | Build staged construction | 3 | CES Engineer
8 | 7 | Seismic Construction Analysis | Analysis for seismic construction | 3 | CES Engineer
9 | 8 | Construction Stage Analysis | Sequential stress check | 5 | CES Engineer
10 | 9 | SLS Analysis | Analysis for service coondition | 5 | CES Engineer
11 | 10 | Report Preparation | Report / PPT | 8 | CES Engineer
12 | 4 | Jacking force | Pressure jack calculation | 7 | Supporting Engineer
37

## SD
task_id | dependencies | task_group | task_description | duration_days | role
1 |  | Gambar Struktur | Gambar struktur utama secara keseluruhan | 2 | Drafter
2 | 1 | Holes Location | Plotting lubang spare FT | 2 | Drafter
3 | 2 | Skematik tendon | Gambar Skematik | 2 | Drafter
4 | 3 | Tendon top plan | Gambar tampak denah tendon top | 4 | Drafter
5 | 4 | Tendon bottom plan | Gambar tampak denah tendon bottom | 4 | Drafter
6 | 5 | Side view tendon top & coordinates | Gambar tampak samping tendon top dan koordinat Y1, Y2, dan Z | 6 | Drafter
7 | 6 | Side view tendon bottom & coordinates | Gambar tampak samping tendon bottom dan koordinat Y1, Y2, dan Z | 6 | Drafter
8 | 7 | Detailing | Gambar detailing seperti pembesian angkur, blister dan lain lain | 4 | Drafter
30

## FT
task_id | dependencies | task_group | task_description | duration_days | role
1 |  | Cek part/detailing | Gambar struktur utama secara keseluruhan | 2 | FT Engineer
2 | 1 | FT Loadings | Perhitungan beban FT dari box girder | 3 | FT Engineer
3 | 2 | FT Bottom | Analisa FT Bottom | 3 | FT Engineer
4 | 3 | FT Drive deck & cantilever | analisa struktur drive deck dan kantilever | 3 | FT Engineer
5 | 4 | FT Main Frame | Analisa struktur man frame | 5 | FT Engineer
6 | 5 | PPT Report | Reporting dalam bentuk ppt | 5 | FT Engineer
21